KIMI  AMPLIRAIL 2.0

KIMI opinion 1 , after reviewing the development docs :

# Sprint 0.5 Tickets: The 4-Day Activation Engine

AR-168 to AR-174  |  Add-on series to docs/BACKLOG.md  |  Epic: Onboarding and activation

| Version | 1.0 ¦ October 4, 2026 |
| --- | --- |
| Status | Ready to load into GitHub Issues |
| Owner | Lead eDataPay PHP Developer (technical owner) |
| Platform owner | Adam Elisha, Systems Administrator / Platform Owner |
| Source documents | AmpliRail 2.0 Master Development Document V3.7; eDataPay 4-Day Merchant Activation System Design V3.7 |
| Format | Every ticket follows docs/TASK_TEMPLATE.md and the Definition of Done in master document Section 21 |

## How to use this document

These seven tickets turn the 4-Day Merchant Activation design into executable work. They close the gap between the activation blueprint and the existing backlog (AR-001 to AR-167), which covers the rail, connectors, fees and screens but has no build units for the activation engine itself.

### Run order (dependencies)

AR-174 first. It resolves the two V3.7 document conflicts that every later ticket depends on.

AR-168, then AR-171. This is the Day 0 spine: CRM handoff plus the event catalog.

AR-169 and AR-170 in parallel, in separate git worktrees (Start Guide Step 14).

AR-172, then AR-173 last, because the dashboard reads state the other tickets write.

### The developer operating model (one instruction)

Start every session with prompt P0, execute with P1, review with P6 (and P5 where a ticket is marked security-relevant). One ticket per session, one branch per ticket. No real card data, no secrets in chat, simulator only. A human approves every merge.

Developers do not need the full master document in their heads. Each session needs only the ticket and the three files P0 loads automatically: AGENTS.md, the master document, SECURITY.md.

## Series at a glance

| Ticket | What it builds | Why it runs when it runs |
| --- | --- | --- |
| AR-174 | ADR resolving the RoboRisk boundary and sandbox provisioning state conflicts | Nothing should be coded against two conflicting documents |
| AR-168 | CRM handoff API plus Day 0 auto-provisioning (sandbox MID, API keys, webhook secret) | The spine the whole 4-day clock hangs on |
| AR-171 | The 12 onboarding events wired into the outbox behind a strict state machine | Makes every step auditable and powers the dashboard |
| AR-169 | Document checklist engine, data-driven per processor | Parallel with AR-170 via worktrees |
| AR-170 | Processor eligibility rules engine | Stops staff building packages for routes that cannot take them |
| AR-172 | Go-live gate with dual control | The money-moving control point; fail-closed |
| AR-173 | SLA command center on the admin Overview screen | Makes blockers, owners and deadlines visible |

## Ticket AR-168: CRM handoff API and Day 0 sandbox auto-provisioning

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Test |
| Plan first | Yes |
| Security-relevant | Yes (auth, tenancy, idempotency, PII) |
| Screens | Add merchant (AR-016, AR-051) |
| Depends on | AR-174 |

### Goal

The Fintech CRM hands a merchant application to AmpliRail through one idempotent API call. On receipt, AmpliRail creates the permanent merchant record (preserving crm_deal_id), moves it to submitted, and automatically provisions a sandbox MerchantAccount on the simulator, a test MID, a sandbox API key pair (arpub_sbx_ / arsec_sbx_) and a webhook secret (arwhk_sbx_).

### Context

Master document Sections 6, 10 and 13; 4-Day Activation document Sections 3 and 11 (one permanent eDataPay Merchant ID; Day 0 objective). Per the ADR in AR-174, sandbox is provisioned at submitted, not approved.

### Scope: files allowed to change

modules/Onboarding/ (Domain, Application, Infrastructure, Http, Contracts, Tests)

modules/Identity/ (API key issuance only, via its Contracts interface)

openapi/ (new POST /v1/merchants/handoff endpoint)

tests/ (feature and tenant-isolation tests)

### Out of scope

CRM code (separate system; we only define the contract it calls)

Production credentials of any kind; sandbox only

RoboRiskAnalysis internals (reached only through the RiskDecision connector)

Any change to the processor connectors

### Acceptance criteria

1. POST /v1/merchants/handoff accepts the minimum application package from the 4-Day document Section 3 (legal name, DBA, EIN, addresses, owners/UBOs, settlement bank token reference, website, MCC request, volume and ticket estimates, channels, documents, agent attribution) and requires an Idempotency-Key header.

2. crm_deal_id is stored immutable; a second handoff with the same crm_deal_id returns the existing merchant, never a duplicate.

3. On first creation the merchant enters submitted and, in the same transaction, receives a simulator MerchantAccount, test MID, sandbox API key pair and webhook secret. All four appear on the merchant record.

4. Every creation, state change and provisioning step writes an outbox event (application.created, merchant.submitted, merchant.sandbox_provisioned) in the same database transaction.

5. The endpoint authenticates with OAuth2 client credentials scoped to the CRM service only; it is not reachable with merchant or admin portal sessions.

6. Validation rejects packages missing minimum fields with the standard error shape; nothing is created on rejection.

### Tests required

Unit: idempotency replay on repeated key and repeated crm_deal_id

Feature/API: full happy path; validation failures; partial package rejection

Tenant isolation: CRM credentials for one org cannot hand off into another; sibling nodes cannot see the merchant

Failure modes: provisioning retry never duplicates MIDs or keys; rollback leaves no orphan records

### Security considerations

PII (owners, EIN) encrypted with KMS envelope encryption; tax ID field-encrypted with fingerprint for matching. Fail closed: no tenant context, no handoff. No PAN, CVV or bank account numbers in the payload; bank data arrives as a token reference. Structured logs with correlation ID; PII masked.

### Rollback

Feature flag crm_handoff (off in staging and production until pilot). Migration down removes the endpoint registration; created merchant records remain valid data.

## Ticket AR-169: Document checklist engine

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Test |
| Plan first | Yes |
| Security-relevant | Yes (encrypted storage, access control) |
| Screens | Merchant 360 |
| Depends on | AR-174 |

### Goal

A configurable checklist engine tracks which documents each merchant must provide at each onboarding stage, knows when the set is complete, and emits documents.complete. Requirements are data-driven per processor and merchant profile, never hard-coded.

### Context

4-Day Activation document Sections 3 and 6 (documents.complete event; processor more-info requests). Master document Section 10 (onboarding saga) and Section 15 (document storage rules).

### Scope: files allowed to change

modules/Onboarding/ (checklist domain)

Encrypted object storage via the existing storage service

openapi/ (GET/POST /v1/merchants/{id}/documents)

tests/

### Out of scope

Document content analysis (RoboRiskAnalysis does that through its own connector)

KYB vendor calls (KYB simulator connector only at this stage)

### Acceptance criteria

1. Checklist requirements are configuration rows: document type, required stage, applies-to rules (MCC, processor route, channel, volume).

2. Uploads store encrypted in private S3 with KMS; metadata in PostgreSQL; every download is permission-checked and audited.

3. Completeness is evaluated on every upload and removal; when the required set for the current stage is complete, documents.complete is written to the outbox.

4. Processor more_info_required responses (via the boarding connector) add requirements dynamically and reopen the checklist.

5. Admins see checklist state on Merchant 360; merchants see outstanding items in the portal.

### Tests required

Unit: rule evaluation; checklist state transitions

Feature: upload, complete, reopen on processor request

Abuse case: path traversal in upload names rejected; oversized and wrong-type files rejected; no public URLs

Tenant isolation: one merchant’s documents never readable by another

### Security considerations

Documents are PII and KYB evidence: encrypted at rest, TLS in transit, no execution. Any download URL is signed with short expiry. Audit every view and download.

### Rollback

Feature flag document_checklist. Configuration rows are inert without the module.

## Ticket AR-170: Processor eligibility rules engine

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Test |
| Plan first | Yes |
| Security-relevant | No |
| Screens | Routing |
| Depends on | AR-174 |

### Goal

Before staff submit a merchant to a processor, a data-driven rules engine ranks which configured acquirers and processors can accept the merchant, so no one builds a submission package for a route that cannot take it.

### Context

4-Day Activation document Section 5. Master document Section 8 (eligibility filter is the first routing stage) and Section 7 (connector manifests declare capabilities, currencies, brands, channels, 3DS).

### Scope: files allowed to change

modules/Routing/ (eligibility domain only; does not touch the scoring stage)

openapi/ (GET /v1/merchants/{id}/eligibility)

tests/

### Out of scope

Submission itself (MerchantBoarding connector work is a later sprint)

Routing policy scoring and failover (existing Section 8 tickets)

### Acceptance criteria

1. Rules are configuration: geography, MCC and restricted categories, card-present vs card-not-present, recurring, volume, ticket size, chargeback profile, currency, reserve requirements, processor document requirements.

2. The engine returns an ordered, explainable list of eligible routes, with the rule outcomes stored on the merchant record.

3. Ineligible routes return the specific failing rules, not just a refusal.

4. Rule changes are versioned and effective-dated; publishing goes through the Approvals service, never a direct edit.

### Tests required

Unit: each rule type, rule precedence, versioning

Feature: a standard eCommerce merchant, a restricted MCC, and a high-volume merchant

Contract: engine output consumed correctly by the existing routing eligibility filter

### Security considerations

Rules are commercial configuration; changes are audited with before and after values.

### Rollback

Feature flag eligibility_engine. The manual choice path remains available.

## Ticket AR-171: Onboarding event catalog wiring

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Test |
| Plan first | No |
| Security-relevant | Yes (outbox integrity) |
| Screens | Merchant 360, Transactions |
| Depends on | AR-168 |

### Goal

The twelve merchant lifecycle events from the 4-Day Activation document exist as real, emitted, immutable outbox events with matching state-machine transitions: application.created, documents.complete, kyb.passed, risk.approved, processor.submitted, processor.more_info_required, processor.approved, mid.created, credentials.created, test.completed, merchant.live, plus merchant.sandbox_provisioned from AR-168.

### Context

4-Day Activation document Section 6 (event table). Master document Section 6 (merchant state machine) and Section 11 (outbox and event envelope).

### Scope: files allowed to change

modules/Onboarding/ (state machine transitions, outbox writes)

modules/Audit/ (only if an event type is missing from its schema)

openapi/ (event payloads)

tests/

### Out of scope

Events already emitted by Payments and Ledger (master document Section 11)

Webhook delivery mechanics (AR-021)

### Acceptance criteria

1. Each of the 12 events fires exactly once per occurrence, written in the same transaction as the state change that causes it.

2. Illegal state jumps are impossible: every transition lives in one state machine class and throws (and logs) otherwise.

3. Each event carries the Section 11 envelope: correlation ID, actor, org path, environment, subject, data.

4. The Merchant 360 event timeline renders the full sequence for a merchant that runs CRM handoff to go-live.

### Tests required

Unit: every legal transition; at least one illegal transition per state

Feature: full lifecycle emits the 12 events in order with correct payloads

Idempotency: replaying a transition never duplicates events

### Security considerations

Events are immutable and consumers are idempotent. No PII beyond the envelope schema; documents are referenced by ID, never by content.

### Rollback

Events are additive; rollback is disabling consumers that depend on the new event types.

## Ticket AR-172: Automated go-live gate with dual control

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Test |
| Plan first | Yes |
| Security-relevant | Yes (dual control, permissions, money) |
| Screens | Approvals, Merchant 360 |
| Depends on | AR-168, AR-171 |

### Goal

A merchant cannot move from test_mode to active until a system-enforced checklist passes and a second authorized human approves. AI agents never activate production processing.

### Context

4-Day Activation document Section 9 (go-live gate, dual control, checklist). Master document Section 5.3 (merchants.go_live.approve), Section 10 (go-live step of the saga), Section 18 (AI never activates production).

### Scope: files allowed to change

modules/Onboarding/ (gate evaluation and transition)

Approvals integration (via its Contracts interface only)

openapi/ (/v1/merchants/{id}/request_go_live and approval endpoints)

tests/

### Out of scope

Live credential provisioning (a later connector sprint). The gate records and enforces the checkpoint; it does not issue credentials.

### Acceptance criteria

1. Gate checklist, all data-driven and verified live: underwriting decision recorded; processor approval and production MID/TID recorded; credentials stored via the secrets process; test sale passed; refund and void path validated; webhook delivery validated; settlement configuration verified; risk limits, reserve and descriptor confirmed; PCI status recorded.

2. All checks green opens an Approvals item. The approver must hold merchants.go_live.approve, must be a different person than the requester, and must enter a step-up code and a note.

3. Approval transitions the merchant to active and emits merchant.live; anything missing keeps the merchant in test_mode with the failing checks visible.

4. The gate is fail-closed: if any check cannot be evaluated (connector down, data missing), the check fails.

### Tests required

Feature: full pass; each single failing check blocks activation

Authorization: requester cannot approve own request; users without the permission cannot approve; cross-tenant approver blocked

Abuse case: calling the state transition directly without Approvals throws and is logged

### Security considerations

This is a money-moving control point. Dual control is enforced in code, not only in the UI. Every gate evaluation is audited with actor, timestamp and the data each check relied on.

### Rollback

Feature flag go_live_gate. If disabled, merchants remain activatable through the existing manual path; the flag state itself is audited.

## Ticket AR-173: Merchant activation SLA command center

| Sprint | 0.5 |
| --- | --- |
| Agent role | Builder / Docs |
| Plan first | No |
| Security-relevant | No |
| Screens | Overview |
| Depends on | AR-172 |

### Goal

The admin Overview gains an onboarding pipeline view that makes the blocker, owner, next action and deadline obvious for every in-flight merchant, with median time-in-state, time-to-live, SLA-at-risk cases and connector and webhook health.

### Context

4-Day Activation document Section 12. Master document Section 12.1 (Overview screen) and Section 23 (metrics).

### Scope: files allowed to change

Admin console Overview (reads existing API endpoints only; no direct DB access from the UI, per prompt P10)

openapi/ (one read-only aggregation endpoint if needed)

tests/

### Out of scope

Editing merchant state from this screen (actions stay on their own screens)

### Acceptance criteria

1. Pipeline counts per state (New, KYB/KYC, Risk, Processor, Test, Live) with day-over-day change.

2. Per-merchant rows: state, days in state, blocker, owner, next action, deadline; SLA-at-risk rows highlighted.

3. Median and average time per state and total time-to-live for the last 90 days.

4. Reads reflect data written by AR-168 to AR-172; sample-data mode for demos.

### Tests required

Feature: each role that should see the command center sees it; roles that should not, do not; figures match fixture data exactly

### Security considerations

Read-only, permission-checked (merchants.view). No PII beyond merchant name and IDs already visible in the Merchants list.

### Rollback

Remove the dashboard section; the underlying APIs remain.

## Ticket AR-174: ADR — RoboRisk deployment boundary and sandbox provisioning state

| Sprint | 0.5 |
| --- | --- |
| Agent role | Architect |
| Plan first | Yes |
| Security-relevant | Yes (PCI scope) |
| Screens | n/a |
| Runs | FIRST in this series, before any code ticket |

### Goal

One accepted ADR that resolves the two V3.7 document conflicts before AR-168 and later tickets are built, so every agent and developer works from one answer.

### Context

Conflict 1: master document D18 and Section 10.2 define RoboRiskAnalysis as a separate product (own repo, domain, AWS account and database, outside card-data scope). The 4-Day Activation document describes RoboRisk as a Laravel module and connector layer.

Conflict 2: the master state machine provisions the sandbox on approved; the 4-Day model provisions on application creation (Day 0).

### Scope: files allowed to change

docs/adr/ADR-0004-roborisk-boundary-and-sandbox-state.md

One-line clarifying edits to master document Section 10.2 and Section 6, and to the 4-Day Activation document Section 4, once the ADR is accepted.

### Out of scope

Any code

Any change to the RiskDecision connector contract itself

### Acceptance criteria

1. The ADR records: RoboRiskAnalysis is built in Laravel/PHP but deployed as its own product (own repo roboriskanalysis, own AWS account and database, no card data ever). AmpliRail integrates exclusively through the RiskDecision connector and consumes risk.* events. No RoboRisk domain logic inside the AmpliRail monolith beyond the connector and its tests.

2. The ADR records: sandbox MerchantAccount, test MID, API key pair and webhook secret are provisioned automatically at the submitted state, and the master document state machine description is updated to match.

3. Options considered (at least two per decision), consequences, PCI and security impact, and rollback path are documented in under two pages.

4. Marked Accepted only after the Lead eDataPay PHP Developer and Adam approve; until then it is Proposed and agents build to the stated defaults.

### Tests required

None (documentation). Verification is human review by both approvers.

### Security considerations

The PCI scope decision is the point of this ADR: keeping RRA in a separate account and network is what keeps it outside the QSA’s card-data boundary.

### Rollback

Revert the three one-line document edits; the ADR remains in the log as superseded.

## Loading these tickets into GitHub

Create one Issue per ticket using .github/ISSUE_TEMPLATE/ticket.md and the rows above; title format "AR-168: CRM handoff API and Day 0 sandbox auto-provisioning".

Labels: ticket, sprint-0.5, plan-first (AR-168, AR-169, AR-170, AR-172, AR-174), security-relevant (AR-168, AR-169, AR-171, AR-172, AR-174).

Project board order: AR-174 in Ready first, then AR-168, AR-171, AR-169 and AR-170, then AR-172, AR-173.

## What only the humans can unblock

Adam’s five launch-slice decisions: NMI sandbox and production API access; Gattera API documentation and sandbox; counsel-approved merchant and fee agreement wording; pilot merchant list; Elavon SE session date.

The real GitHub username behind Lead eDataPay PHP Developer added to rail-owners before the first session.

Note on timing: this series builds a correct activation spine, but first live payments still depend on the Sprint 0 and Sprint 1 simulator tickets (AR-001 to AR-025) being green. Run Sprint 0 and Sprint 0.5 in parallel, not sequentially. That is the fastest safe path to live.

# V3.7.1 Corrections - Controlling

AR-168 authentication: use the approved AmpliRail machine-auth mechanism. OAuth2 client credentials are required only where the Identity module already supports them.

AR-172 rollback/failure behavior: fail closed. If the go-live gate is disabled or unavailable, merchants cannot transition to active. Emergency override requires Platform Owner authorization plus a second authorized human, step-up authentication, a mandatory reason and an immutable audit event.